## Slide 1
Portsmouth Square
Restroom Replacement
Community Meeting #5
January 8, 2013

## Slide 2
Welcome
欢迎

## Slide 3
Agenda
Welcome
Ground Rules
Purpose of Meeting
Project Background
Project History
Planning Process & Schedule
Basis for Revisions
Program Requirements
Design Revisions Presentation
Public Comments & Discussions
Next Steps

## Slide 4
Ground Rules
Keep to the agenda
Turn off cell phones & pagers
Disruptions will NOT be tolerated
Raise your hand to speak
Direct comments to the facilitator
Working together will make this a productive meeting!

## Slide 5: AERIAL VIEW
RESTROOM LOCATION

## Slide 6
Purpose of Meeting
To provide a project update; and to solicit feedback on design revisions for a new restroom facility at Portsmouth Square.
(Please direct facility maintenance questions to Carol Sionkowski at Carol.Sionkowski@sfgov.org. Thank you.)

## Slide 7
Project Background
2008 “Clean and Safe” Park Bond
  Restroom Program
  $11.4 million
  21 existing sites
  Renovate, replace and new
  $650,000 construction for Portsmouth Sq.
Project Team (Marvin Yee, Project Manager)
  Recreation and Park Dept.
  Chinatown CDC
  Hamilton+Aitken Architects

## Slide 8
Project History
Preliminary Planning
  Site Analysis
  RPD Staff
  Neighborhood Organizations
    Chinatown CDC
    Self-Help for the Elderly
    Portsmouth Square Garage
    Chinese for Affirmative Action
Community Meetings

## Slide 9
Planning Process & Schedule
Community Meetings
  Meeting #1 – Introduction and Public Input
  Meeting #2 (8/30/12) – Massing Studies and Design Ideas
  Meeting #3 (9/20/12) – Plan and Design Alternatives
  Meeting #4 (10/4/12) – Final Plan and Design
  Meeting #5 (1/8/13) – Update and Design Revisions
RecPark Commission Approval (Oct 2012)
Arts Commission Approval
  Phase 1 Review (10/15/12 & 12/17/12) – Initial Concept
  Phase 2 Review (1/14/13) – Finalize Concept and Materials
  Phase 3 Review (2/18/13) – Construction Documents
Bid and Award (Mar – Jun 2013)
Construction (Aug – Dec 2013)
Completion – Grand Opening !!!

## Slide 10
Basis for Revisions
Arts Commission Review
  Roofed pavilion as basic structure
  Blur the edges of indoor/outdoor spaces
  Create outdoor seating
  Study a shed-roof option
Construction budget of $650K
  Previous design estimated at $900K
  More efficient building footprint
  Increased men’s room capacity

## Slide 11
Program Requirements
Increase capacity
Ensure user privacy
Maintain storage
Preserve performance space
Consider pedestrian circulation
Avoid hidden spaces

## Slide 12: INSERT H+A SLIDES

## Slide 13
Thank you!
谢谢 !